## Detailing Chart
Column1 | Column2
45 | Total Projects
0 | Error Projects
0 | No-Error Projects
0% | Error Percentages
0% | No-Error Percentages

## Detailing
0
Project ID | Level | Date Started | Complete | Corrected (Initial Detailing) | Due Date | Send Date | Error Level | Issue | Error Date | Error | Error Tracking
7324 | 4: Core and Coil | 2024-12-16 | 2024-12-16 | 2024-12-26 | 2025-04-03 | 2025-05-23 |  |  |  |  | 0
7324 | 12: Nameplate | 2024-12-16 | 2024-12-16 | 2024-12-26 | 2025-04-03 | 2025-05-23 |  |  |  |  | 0
7336 | 10: Reactor Cleat & Lead | 2024-12-18 | 2024-12-18 | 2024-12-19 | 2025-04-09 | 2025-06-11 |  |  |  |  | 0
7211 | 13: Design | 2024-12-21 |  |  | 2025-09-30 | 2025-11-21 |  |  |  |  | 0
7211 | 12: Nameplate | 2024-12-28 | 2025-02-03 | 2025-02-03 | 2025-09-30 | 2025-11-21 |  |  |  |  | 0
6330 | 8: LV Cleat & Lead | 2024-12-31 | 2024-12-31 | 2025-01-06 | 2025-10-20 | 2025-06-26 |  |  |  |  | 0
7323 | 4: Core and Coil | 2025-01-03 | 2025-01-03 | 2025-01-06 | 2025-05-15 | 2025-09-10 |  |  |  |  | 0
6870 | 9: Internal | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-07-31 | 2025-09-15 |  |  |  |  | 0
6857 | 5: Core Stacking | 2025-01-08 | 2025-01-08 | 2025-01-13 | 2025-04-21 | 2025-07-22 |  |  |  |  | 0
6857 | 6: E-Assembly | 2025-01-08 | 2025-01-08 | 2025-01-13 | 2025-04-21 | 2025-07-22 |  |  |  |  | 0
7269 | 8: LV Cleat & Lead | 2025-01-15 | 2025-01-15 | 2025-01-16 | 2025-04-25 | 2025-06-27 |  |  |  |  | 0
7269 | 10: Reactor Cleat & Lead | 2025-01-15 | 2025-01-15 | 2025-01-16 | 2025-04-25 | 2025-06-27 |  |  |  |  | 0
6887 | 9: Internal | 2025-01-17 | 2025-01-17 | 2025-01-22 | 2025-05-14 | 2025-06-27 |  |  |  |  | 0
7318 | 5: Core Stacking | 2025-01-22 | 2025-01-22 | 2025-01-22 | 2025-05-21 | 2025-07-30 |  |  |  |  | 0
7318 | 7: HV Cleat & Lead | 2025-01-22 | 2025-01-22 | 2025-01-22 | 2025-05-21 | 2025-07-30 |  |  |  |  | 0
7318 | 12: Nameplate | 2025-01-22 | 2025-01-22 | 2025-01-22 | 2025-05-21 | 2025-07-30 |  |  |  |  | 0
7241 | 4: Core and Coil | 2025-01-23 | 2025-01-23 | 2025-01-30 | 2025-05-30 | 2025-08-07 |  |  |  |  | 0
7241 | 7: HV Cleat & Lead | 2025-01-23 | 2025-01-23 | 2025-01-30 | 2025-05-30 | 2025-08-07 |  |  |  |  | 0
7241 | 8: LV Cleat & Lead | 2025-01-23 | 2025-01-23 | 2025-01-30 | 2025-05-30 | 2025-08-07 |  |  |  |  | 0
6900 | 4: Core and Coil | 2025-01-31 | 2025-02-03 | 2025-02-04 | 2025-07-21 | 2025-09-03 |  |  |  |  | 0
6900 | 7: HV Cleat & Lead | 2025-01-31 | 2025-02-03 | 2025-02-04 | 2025-07-21 | 2025-09-03 |  |  |  |  | 0
7224 | 3: Booster Cleat & Lead | 2025-02-10 | 2025-02-11 | 2025-02-18 | 2025-06-17 | 2025-08-25 |  |  |  |  | 0
7224 | 4: Core and Coil | 2025-02-10 | 2025-02-11 | 2025-02-18 | 2025-06-17 | 2025-08-25 |  |  |  |  | 0
6279 | 4: Core and Coil | 2025-02-11 | 2025-02-18 | 2025-02-18 | 2025-06-12 | 2025-08-01 |  |  |  |  | 0
6279 | 8: LV Cleat & Lead | 2025-02-11 | 2025-02-18 | 2025-02-18 | 2025-06-12 | 2025-08-01 |  |  |  |  | 0
7164 | 1: Air Reactor | 2025-02-12 | 2025-02-25 | 2025-02-27 | 2025-06-20 | 2025-09-22 |  |  |  |  | 0
7164 | 4: Core and Coil | 2025-02-12 | 2025-02-25 | 2025-02-27 | 2025-06-20 | 2025-09-22 |  |  |  |  | 0
7164 | 7: HV Cleat & Lead | 2025-02-12 | 2025-02-25 | 2025-02-27 | 2025-06-20 | 2025-09-22 |  |  |  |  | 0
7295 | 4: Core and Coil | 2025-03-07 | 2025-03-11 | 2025-03-11 | 2025-06-23 | 2025-08-29 |  |  |  |  | 0
7351 | 4: Core and Coil | 2025-03-14 | 2025-03-14 | 2025-03-17 | 2025-06-23 | 2025-08-12 |  |  |  |  | 0
7351 | 8: LV Cleat & Lead | 2025-03-14 | 2025-03-14 | 2025-03-17 | 2025-06-23 | 2025-08-12 |  |  |  |  | 0
6914 | 6: E-Assembly | 2025-03-19 | 2025-03-26 | 2025-04-15 | 2025-09-19 | 2025-12-16 |  |  |  |  | 0
7422 | 7: HV Cleat & Lead | 2025-03-27 | 2025-03-31 | 2025-04-09 | 2025-07-16 | 2025-09-17 |  |  |  |  | 0
7422 | 8: LV Cleat & Lead | 2025-03-27 | 2025-03-31 | 2025-04-09 | 2025-07-16 | 2025-09-17 |  |  |  |  | 0
7415 | 3: Booster Cleat & Lead | 2025-03-28 | 2025-04-09 | 2025-04-10 | 2025-08-21 | 2025-10-06 |  |  |  |  | 0
7415 | 4: Core and Coil | 2025-03-28 | 2025-04-09 | 2025-04-10 | 2025-08-21 | 2025-10-06 |  |  |  |  | 0
7415 | 6: E-Assembly | 2025-03-28 | 2025-04-10 | 2025-04-11 | 2025-08-21 | 2025-10-06 |  |  |  |  | 0
7415 | 7: HV Cleat & Lead | 2025-03-28 | 2025-04-09 | 2025-04-10 | 2025-08-21 | 2025-10-06 |  |  |  |  | 0
7415 | 8: LV Cleat & Lead | 2025-03-28 | 2025-04-09 | 2025-04-10 | 2025-08-21 | 2025-10-06 |  |  |  |  | 0
7415 | 11: Top Rack | 2025-03-28 | 2025-04-09 | 2025-04-10 | 2025-08-21 | 2025-10-06 |  |  |  |  | 0
7362 | 8: LV Cleat & Lead | 2025-04-02 | 2025-04-07 | 2025-04-08 | 2025-07-08 | 2025-08-20 |  |  |  |  | 0
6471 | 7: HV Cleat & Lead | 2025-04-04 | 2025-04-04 | 2025-04-05 | 2025-06-19 | 2025-08-27 |  |  |  |  | 0
7443 | 13: Design | 2025-04-07 |  |  | 2026-01-26 | 2026-03-10 |  |  |  |  | 0
7443 | 12: Nameplate |  |  |  | 2025-07-25 | 2025-08-08 |  |  |  |  | 0
7122 | 12: Nameplate | 2025-03-10 | 2025-04-15 |  | 2025-02-15 | 2026-02-15 |  |  |  |  | 0
Formulas:
Error = IF(TODAY()<[Send Date], "", IF(ISNUMBER(SEARCH("No Issue", [Issue])), "NO", "YES"))

## Sheet1
1: Air Reactor | 1: NC
2: Booster | 2: OCR
3: Booster Cleat & Lead | 3: No Issues
4: Core and Coil
5: Core Stacking
6: E-Assembly
7: HV Cleat & Lead
8: LV Cleat & Lead
9: Internal
10: Reactor Cleat & Lead
11: Top Rack
12: Nameplate
13: Design