## Dashboard
Column1 | Column2
98 | Total Projects
32 | Error Projects
17 | No-Error Projects
32.65% | Error Percentages
17.35% | No-Error Percentages

## Projects
Project ID | Level | Date Started | Complete | Working Days | Corrected (Initial Detailing) | Correction Time | Due Date | Send Date | Days Remain | Status | Job done | Delay Category | Delay Reason | Error Date | ID Number | Issue | Error | Error Tracking
6511 | Nameplate | 2025-03-19 | 2025-03-21 | 2 | 2025-03-21 | 0 | 2025-03-21 | 2025-03-21 | -196 | Completed | On Time |  |  | 2025-03-19 | OCR14223 | OCR | YES | 1
6802 | Nameplate | 2025-04-10 | 2025-05-15 | 35 | 2025-05-15 | 0 | 2025-04-14 | 2025-04-14 | -172 | Completed | Late | Communication Delay | Waiting on DE to respond to email. OCR does not have any markups on the nameplate. No errors on nameplate. DE closed OCR on 5/15/25 | 2025-05-15 | OCR14238 | OCR | NO | 0
6511 | LV Cleat & Lead (Old Style) | 2024-09-17 | 2024-09-17 | 0 | 2024-09-25 | 8 | 2025-04-30 | 2025-04-30 | -156 | Completed | On Time |  |  |  |  | No Issues | NO | 0
6511 | Nameplate | 2025-04-30 | 2025-04-30 | 0 | 2025-04-30 | 0 | 2025-04-30 | 2025-04-30 | -156 | Completed | On Time |  |  | 2025-04-30 | NC4044770 | NC | YES | 2
7241 | Internal Recheck | 2025-05-02 | 2025-05-07 | 5 | 2025-05-07 | 0 | 2025-05-07 | 2025-05-07 | -149 | Completed | On Time |  |  | 2025-05-02 |  | Recheck | YES | 0
6331 | Nameplate | 2025-04-30 | 2025-04-30 | 0 | 2025-04-30 | 0 | 2025-05-09 | 2025-05-09 | -147 | Completed | On Time |  |  | 2025-04-29 | OCR14252 | OCR | YES | 1
6332 | Nameplate | 2025-04-30 | 2025-04-30 | 0 | 2025-04-30 | 0 | 2025-05-09 | 2025-05-09 | -147 | Completed | On Time |  |  | 2025-04-29 | OCR14252 | OCR | YES | 1
7351 | Internal Recheck | 2025-05-09 | 2025-05-09 | 0 | 2025-05-09 | 0 | 2025-05-09 | 2025-05-09 | -147 | Completed | On Time |  |  | 2025-05-09 |  | Recheck | YES | 0
6779 | Nameplate | 2024-12-18 | 2025-01-06 | 19 | 2025-01-06 | 0 | 2025-05-12 | 2025-05-12 | -144 | Completed | On Time |  |  |  |  | No Issues | NO | 0
6158 | Nameplate | 2025-05-13 | 2025-05-13 | 0 | 2025-05-13 | 0 | 2025-05-13 | 2025-05-13 | -143 | Completed | On Time |  |  | 2025-05-13 | NC4045107 | NC | YES | 2
7324 | Core and Coil | 2024-12-16 | 2024-12-16 | 0 | 2024-12-26 | 10 | 2025-04-03 | 2025-05-23 | -183 | Completed | On Time |  |  |  |  | No Issues | NO | 0
7324 | Nameplate | 2024-12-16 | 2024-12-16 | 0 | 2024-12-26 | 10 | 2025-04-03 | 2025-05-23 | -183 | Completed | On Time |  |  |  |  | No Issues | NO | 0
7542 | Nameplate | 2025-05-20 | 2025-05-20 | 0 | 2025-05-20 | 0 | 2025-05-19 | 2025-06-02 | -137 | Completed | Late | Communication Delay | Had to wait on DE to confirm which folder to put nameplate in. Project was not shown on 5722 VCE. |  |  | No Issues | NO | 0
7336 | Reactor Cleat & Lead | 2024-12-18 | 2024-12-18 | 0 | 2024-12-19 | 1 | 2025-04-09 | 2025-06-11 | -177 | Completed | On Time |  |  |  |  | No Issues | NO | 0
6330 | LV Cleat & Lead (Old Style) | 2024-12-31 | 2024-12-31 | 0 | 2025-01-06 | 6 | 2025-10-20 | 2025-06-26 | 17 | Completed | On Time |  |  | 2025-05-21 | ECM 500000017712 | ECM | YES | 0
7269 | LV Cleat & Lead (Old Style) | 2025-01-15 | 2025-01-15 | 0 | 2025-01-16 | 1 | 2025-04-25 | 2025-06-27 | -161 | Completed | On Time |  |  |  |  | No Issues | NO | 0
7269 | Reactor Cleat & Lead | 2025-01-15 | 2025-01-15 | 0 | 2025-01-16 | 1 | 2025-04-25 | 2025-06-27 | -161 | Completed | On Time |  |  |  |  | No Issues | NO | 0
6887 | Internal | 2025-01-17 | 2025-01-17 | 0 | 2025-01-22 | 5 | 2025-05-14 | 2025-06-27 | -142 | Completed | On Time |  |  |  |  | No Issues | NO | 0
6857 | Core Stacking | 2025-01-08 | 2025-01-08 | 0 | 2025-01-13 | 5 | 2025-04-21 | 2025-07-22 | -165 | Completed | On Time |  |  |  |  | No Issues | NO | 0
6857 | E-Assembly | 2025-01-08 | 2025-01-08 | 0 | 2025-01-13 | 5 | 2025-04-21 | 2025-07-22 | -165 | Completed | On Time |  |  |  |  | No Issues | NO | 0
6691 | Nameplate | 2025-05-20 | 2025-07-22 | 63 | 2025-07-22 | 0 | 2025-03-25 | 2025-07-29 | -192 | Completed | Late | Date Moved | Started Job in May |  |  | No Issues | NO | 0
7318 | Core Stacking | 2025-01-22 | 2025-01-22 | 0 | 2025-01-22 | 0 | 2025-05-21 | 2025-07-30 | -135 | Completed | On Time |  |  | 2025-05-16 |  | Client Email | YES | 0
7318 | HV Cleat & Lead | 2025-01-22 | 2025-01-22 | 0 | 2025-01-22 | 0 | 2025-05-21 | 2025-07-30 | -135 | Completed | On Time |  |  |  |  | No Issues | NO | 0
7318 | Nameplate | 2025-01-22 | 2025-01-22 | 0 | 2025-01-22 | 0 | 2025-05-21 | 2025-07-30 | -135 | Completed | On Time |  |  |  |  | No Issues | NO | 0
7561 | Nameplate | 2025-07-22 | 2025-07-23 | 1 | 2025-07-25 | 2 | 2025-08-26 | 2025-07-30 | -38 | Completed | On Time |  |  |  |  | No Issues | NO | 0
6762 | E-Assembly | 2025-07-21 | 2025-07-21 | 0 | 2025-07-31 | 10 | 2025-08-01 | 2025-07-31 | -63 | Completed | On Time | [5 empty] | YES | 0
6279 | Core and Coil | 2025-02-11 | 2025-02-18 | 7 | 2025-02-18 | 0 | 2025-06-12 | 2025-08-01 | -113 | Completed | On Time |  |  |  |  | No Issues | NO | 0
6279 | LV Cleat & Lead (Old Style) | 2025-02-11 | 2025-02-18 | 7 | 2025-02-18 | 0 | 2025-06-12 | 2025-08-01 | -113 | Completed | On Time |  |  | 2025-05-23 | ECM 500000017721 | ECM | YES | 0
7628 | Nameplate | 2025-05-09 | 2025-06-19 | 41 | 2025-06-19 | 0 | 2025-07-22 | 2025-08-05 | -73 | Completed | On Time | [5 empty] | YES | 0
7241 | Core and Coil | 2025-01-23 | 2025-01-23 | 0 | 2025-01-30 | 7 | 2025-05-30 | 2025-08-07 | -126 | Completed | On Time | [5 empty] | YES | 0
7241 | HV Cleat & Lead | 2025-01-23 | 2025-01-23 | 0 | 2025-01-30 | 7 | 2025-05-30 | 2025-08-07 | -126 | Completed | On Time |  |  | 2025-05-21 | ECM 500000017713 | ECM | YES | 0
7241 | LV Cleat & Lead (Old Style) | 2025-01-23 | 2025-01-23 | 0 | 2025-01-30 | 7 | 2025-05-30 | 2025-08-07 | -126 | Completed | On Time | [5 empty] | YES | 0
7351 | LV Cleat & Lead (Old Style) | 2025-03-14 | 2025-03-14 | 0 | 2025-03-17 | 3 | 2025-06-23 | 2025-08-12 | -102 | Completed | On Time | [5 empty] | YES | 0
7362 | LV Cleat & Lead (Old Style) | 2025-04-02 | 2025-04-07 | 5 | 2025-04-08 | 1 | 2025-07-08 | 2025-08-20 | -87 | Completed | On Time | [5 empty] | YES | 0
7224 | Booster Cleat & Lead | 2025-02-10 | 2025-02-11 | 1 | 2025-02-18 | 7 | 2025-06-17 | 2025-08-25 | -108 | Completed | On Time | [5 empty] | YES | 0
7224 | Core and Coil | 2025-02-10 | 2025-02-11 | 1 | 2025-02-18 | 7 | 2025-06-17 | 2025-08-25 | -108 | Completed | On Time | [5 empty] | YES | 0
6471 | HV Cleat & Lead | 2025-04-04 | 2025-04-04 | 0 | 2025-04-05 | 1 | 2025-06-19 | 2025-08-27 | -106 | Completed | On Time | [5 empty] | YES | 0
6900 | Core and Coil | 2025-01-31 | 2025-02-03 | 3 | 2025-02-04 | 1 | 2025-07-21 | 2025-09-03 | -74 | Completed | On Time | [5 empty] | YES | 0
6900 | HV Cleat & Lead | 2025-01-31 | 2025-02-03 | 3 | 2025-02-04 | 1 | 2025-07-21 | 2025-09-03 | -74 | Completed | On Time | [5 empty] | YES | 0
7323 | Core and Coil | 2025-01-03 | 2025-01-03 | 0 | 2025-01-06 | 3 | 2025-05-15 | 2025-09-10 | -141 | Completed | On Time | [5 empty] | YES | 0
7674 | Tank Size | 2025-06-02 | 2025-07-11 | 39 | 2025-07-11 | 0 | 2025-08-11 | 2025-09-11 | -53 | Completed | On Time | [5 empty] | YES | 0
6870 | Internal | 2025-01-03 | 2025-01-04 | 1 | 2025-01-05 | 1 | 2025-07-31 | 2025-09-15 | -64 | Completed | On Time | [5 empty] | YES | 0
7422 | HV Cleat & Lead | 2025-03-27 | 2025-03-31 | 4 | 2025-04-09 | 9 | 2025-07-16 | 2025-09-17 | -79 | Completed | On Time | [5 empty] | YES | 0
7422 | LV Cleat & Lead (Old Style) | 2025-03-27 | 2025-03-31 | 4 | 2025-04-09 | 9 | 2025-07-16 | 2025-09-17 | -79 | Completed | On Time | [5 empty] | YES | 0
7164 | Air Reactor | 2025-02-12 | 2025-02-25 | 13 | 2025-02-27 | 2 | 2025-06-20 | 2025-09-22 | -105 | Completed | On Time | [5 empty] | YES | 0
7164 | Core and Coil | 2025-02-12 | 2025-02-25 | 13 | 2025-02-27 | 2 | 2025-06-20 | 2025-09-22 | -105 | Completed | On Time | [5 empty] | YES | 0
7164 | HV Cleat & Lead | 2025-02-12 | 2025-02-25 | 13 | 2025-02-27 | 2 | 2025-06-20 | 2025-09-22 | -105 | Completed | On Time | [5 empty] | YES | 0
7164 | REACTOR | 2025-02-12 | 2025-02-25 | 13 | 2025-02-27 | 2 | 2025-06-20 | 2025-09-22 | -105 | Completed | On Time | [5 empty] | YES | 0
7164 | AIR REACTOR TOP | 2025-02-12 | 2025-02-25 | 13 | 2025-02-27 | 2 | 2025-06-20 | 2025-09-22 | -105 | Completed | On Time | [5 empty] | YES | 0
7415 | Booster Cleat & Lead | 2025-03-28 | 2025-04-09 | 12 | 2025-04-10 | 1 | 2025-08-21 | 2025-10-06 | -43 | Completed | On Time | [6 empty] | 0
7415 | Core and Coil | 2025-03-28 | 2025-04-09 | 12 | 2025-04-10 | 1 | 2025-08-21 | 2025-10-06 | -43 | Completed | On Time | [6 empty] | 0
7415 | E-Assembly | 2025-03-28 | 2025-04-10 | 13 | 2025-04-11 | 1 | 2025-08-21 | 2025-10-06 | -43 | Completed | On Time | [6 empty] | 0
7415 | HV Cleat & Lead | 2025-03-28 | 2025-04-09 | 12 | 2025-04-10 | 1 | 2025-08-21 | 2025-10-06 | -43 | Completed | On Time | [6 empty] | 0
7415 | LV Cleat & Lead (Old Style) | 2025-03-28 | 2025-04-09 | 12 | 2025-04-10 | 1 | 2025-08-21 | 2025-10-06 | -43 | Completed | On Time | [6 empty] | 0
7415 | Top Rack | 2025-03-28 | 2025-04-09 | 12 | 2025-04-10 | 1 | 2025-08-21 | 2025-10-06 | -43 | Completed | On Time | [6 empty] | 0
7356 | Booster Cleat & Lead | 2025-05-05 | 2025-05-05 | 0 | 2025-05-07 | 2 | 2025-08-28 | 2025-10-13 | -36 | Completed | On Time | [6 empty] | 0
7356 | E-Assembly | 2025-05-05 | 2025-05-05 | 0 | 2025-05-07 | 2 | 2025-08-28 | 2025-10-13 | -36 | Completed | On Time | [6 empty] | 0
7416 | Booster Cleat & Lead | 2025-05-06 | 2025-05-09 | 3 | 2025-05-09 | 0 | 2025-09-09 | 2025-10-22 | -24 | Completed | On Time | [6 empty] | 0
7416 | Core and Coil | 2025-05-09 | 2025-05-09 | 0 | 2025-05-09 | 0 | 2025-09-09 | 2025-10-22 | -24 | Completed | On Time | [6 empty] | 0
6693 | HV Cleat & Lead | 2025-04-24 | 2025-04-28 | 4 | 2025-04-28 | 0 | 2025-08-04 | 2025-10-28 | -60 | Completed | On Time | [6 empty] | 0
6993 | HV Cleat & Lead | 2025-04-24 | 2025-04-25 | 1 | 2025-04-28 | 3 | 2025-08-04 | 2025-10-28 | -60 | Completed | On Time | [6 empty] | 0
7211 | Internal Design | 2025-07-08 | 2025-07-24 | 16 | 2025-07-25 | 1 | 2025-09-30 | 2025-11-12 | -3 | Completed | On Time | [6 empty] | 0
7211 | Tank Size | 2024-12-21 | 2025-02-06 | 47 | 2025-02-06 | 0 | 2025-09-30 | 2025-11-21 | -3 | Completed | On Time | [6 empty] | 0
7211 | Nameplate | 2024-12-28 | 2025-02-03 | 37 | 2025-02-03 | 0 | 2025-09-30 | 2025-11-21 | -3 | Completed | On Time | [6 empty] | 0
7361 | HV Cleat & Lead | 2025-04-29 | 2025-04-29 | 0 | 2025-05-01 | 2 | 2025-10-13 | 2025-11-25 | 10 | Completed | On Time | [6 empty] | 0
7361 | LV Cleat & Lead (Old Style) | 2025-04-30 | 2025-04-30 | 0 | 2025-05-01 | 1 | 2025-10-13 | 2025-11-25 | 10 | Completed | On Time | [6 empty] | 0
7522 | HV Cleat & Lead | 2025-05-13 | 2025-05-14 | 1 | 2025-05-19 | 5 | 2025-09-26 | 2025-12-01 | -7 | Completed | On Time | [6 empty] | 0
6559 | Reactor Cleat & Lead | 2025-05-19 | 2025-05-21 | 2 | 2025-05-22 | 1 | 2025-09-29 | 2025-12-02 | -4 | Completed | On Time | [6 empty] | 0
6914 | E-Assembly | 2025-03-19 | 2025-03-26 | 7 | 2025-04-15 | 20 | 2025-09-19 | 2025-12-16 | -14 | Completed | On Time | [6 empty] | 0
7523 | Core And Coil | 2025-08-06 | 2025-08-06 | 0 | 2025-08-07 | 1 | 2025-08-08 | 2026-01-29 | -56 | Completed | On Time | [6 empty] | 0
7443 | Tank Size | 2025-04-07 | 2025-06-05 | 59 | 2025-06-07 | 2 | 2025-07-25 | 2026-02-12 | -70 | Completed | On Time | [6 empty] | 0
7443 | Internal Design | 2025-06-09 | 2025-07-30 | 51 | 2025-08-22 | 23 | 2026-01-26 | 2026-02-12 | 115 | Completed | On Time | [6 empty] | 0
7122 | Nameplate | 2025-03-10 | 2025-04-15 | 36 | 2025-04-17 | 2 | 2026-02-15 | 2026-02-15 | 135 | Completed | On Time | [6 empty] | 0
7517 | Core And Coil | 2025-08-07 | 2025-08-07 | 0 | 2025-08-08 | 1 | 2025-12-18 | 2026-02-24 | 76 | Completed | On Time | [6 empty] | 0
7517 | E-Assembly | 2025-08-07 | 2025-08-07 | 0 | 2025-08-11 | 4 | 2025-12-18 | 2026-02-24 | 76 | Completed | On Time | [6 empty] | 0
7517 | Reactor Cleat & Lead | 2025-08-08 | 2025-08-11 | 3 | 2025-08-13 | 2 | 2025-12-18 | 2026-02-24 | 76 | Completed | On Time | [6 empty] | 0
6686 | Hv Cleat & Lead | 2025-05-21 | 2025-06-03 | 13 | 2025-06-10 | 7 | 2025-11-26 | 2026-02-26 | 54 | Completed | On Time | [6 empty] | 0
7629 | Tank Size | 2025-07-17 | 2025-07-30 | 13 | 2025-08-04 | 5 | 2025-08-18 | 2026-04-07 | -46 | Completed | On Time | Tank Size Error | Forgot to take the flitch plate support to bushing clearance | 2025-07-31 |  | No Issues |  | 0
7629 | Internal Design | 2025-07-17 | 2025-07-30 | 13 | 2025-09-15 | 47 | 2026-02-23 | 2026-04-07 | 143 | Completed | On Time |  |  |  |  | No Issues |  | 0
7627 | Nameplate | 2025-08-07 | 2025-08-07 | 0 | 2025-08-14 | 7 | 2025-09-15 | 2026-04-07 | -18 | Completed | On Time | [6 empty] | 0
7674 | Internal Design | 2025-06-02 | 2025-07-11 | 39 | 2025-07-11 | 0 | 2026-03-05 | 2026-04-17 | 153 | Completed | On Time | [6 empty] | 0
7270 | LV Cleat & Lead (Old Style) | 2025-04-15 | 2025-04-16 | 1 | 2025-04-17 | 1 | 2026-03-16 | 2026-04-28 | 164 | Completed | On Time | [6 empty] | 0
7270 | LV Cleat & Lead (Old Style) | 2025-04-16 | 2025-04-17 | 1 | 2025-04-17 | 0 | 2026-03-16 | 2026-04-28 | 164 | Completed | On Time | [6 empty] | 0
7270 | E-Assembly | 2025-04-17 | 2025-04-17 | 0 | 2025-04-21 | 4 | 2026-03-16 | 2026-04-28 | 164 | Completed | On Time | [6 empty] | 0
7503 | Nameplate | 2025-03-31 | 2025-03-31 | 0 | 2025-03-31 | 0 | 2026-02-05 | 2026-04-30 | 125 | Completed | On Time |  |  | 2025-05-07 | OCR14259 | OCR |  | 0
7067 | Nameplate | 2025-04-28 | 2025-04-29 | 1 | 2025-04-30 | 1 | 2026-03-12 | 2026-06-05 | 160 | Completed | On Time |  |  |  |  | No Issues |  | 0
6802 | Core And Coil | 2025-08-18 | 2025-08-18 | 0 | 2025-08-19 | 1 | 2025-11-26 | 2026-02-27 | 54 | Completed | On Time | [6 empty] | 0
6802 | E-Assembly | 2025-08-18 | 2025-08-18 | 0 | 2025-08-19 | 1 | 2025-11-26 | 2026-02-27 | 54 | Completed | On Time | [6 empty] | 0
6734 | Hv Cleat & Lead | 2025-08-17 | 2025-08-26 | 9 | 2025-08-27 | 1 | 2025-09-05 | 2026-02-05 | -28 | Completed | On Time | [6 empty] | 0
6779 | E-Assembly | 2025-08-27 | 2025-08-28 | 1 | 2025-08-29 | 1 | 2025-11-17 | 2026-03-10 | 45 | Completed | On Time | [6 empty] | 0
6840 | Hv Cleat & Lead | 2025-09-09 | 2025-09-10 | 1 | 2025-09-12 | 2 | 2025-12-31 | 2026-03-27 | 89 | Completed | On Time | [6 empty] | 0
7429 | Top Rack | 2025-09-17 | 2025-09-17 | 0 | 2025-09-23 | 6 | 2025-12-23 | 2026-03-18 | 81 | Completed | On Time | [6 empty] | 0
7190 | Booster Cleat & Lead | 2025-09-17 | 2025-09-17 | 0 | 2025-09-17 | 0 | 2026-01-09 | 2026-04-06 | 98 | Completed | On Time | [6 empty] | 0
7049 | Hv Cleat & Lead | 2025-09-23 | 2025-09-23 | 0 | 2025-09-24 | 1 | 2025-11-26 | 2026-03-19 | 54 | Completed | On Time | [6 empty] | 0
7649 | Nameplate | 2025-09-30 | 2025-10-01 | 1 | 2025-10-01 | 0 | 2025-10-01 | 2026-06-11 | -2 | Completed | On Time | [6 empty] | 0
7650 | Nameplate | 2025-09-30 | 2025-10-01 | 1 | 2025-10-01 | 0 | 2025-10-01 | 2026-06-11 | -2 | Completed | On Time | [6 empty] | 0
7651 | Nameplate | 2025-09-30 | 2025-10-01 | 1 | 2025-10-01 | 0 | 2025-10-01 | 2026-06-11 | -2 | Completed | On Time | [6 empty] | 0
7503 | Core And Coil | 2025-10-02 | 2025-10-03 | 1 |  |  | 2026-01-13 | 2026-04-30 | 102 | Completed | [7 empty] | 0
Formulas:
Working Days = DATEDIF([Date Started], [Complete], "D")
Correction Time = IF(AND([Complete]<>"", [Corrected (Initial Detailing)]<>""), DATEDIF([Complete], [Corrected (Initial Detailing)], "D"), "")
Days Remain = IF(ISBLANK([Due Date]), "", [Due Date] - TODAY())
Status = IF([Complete]<>"", "Completed", IF([Due Date]<TODAY(), "Overdue", "On Track"))
Error = IF(TODAY()<[Send Date], "", IF(ISNUMBER(SEARCH("No Issue", [Issue])), "NO", "YES"))

## Data
Air Reactor | NC | Communication Delay
Core Coil Booster | OCR | Date Moved
Booster Cleat & Lead | No Issues | Tank Size Error
Core And Coil | Recheck
Core Stacking | Client Email
E-Assembly | ECM
Hv Cleat & Lead
Lv Cleat & Lead (Old Style)
Internal
Reactor Cleat & Lead
Top Rack
Nameplate
Internal Design
Vp Check
Detailing Check
Internal Recheck
Np Peer Check
Lv Cleat & Lead Top
Lv Cleat & Lead Bot
Tank Size